**Agenda**

**Week 5:**

11/12/2023

Work done today:

* Get to know each other
* Share findings from GA1
* Finished hypothesis formulation (together)
* Started hypothesis refinement (together)

Plans for work until the next meeting:

* Obtain necessary datasets
* Clean datasets
* Finish hypothesis refinement (Kyra + Sven)

Questions from the group:

How should we delegate the tasks?

What to do when you are not here for a meeting?

**Week 6:**

Date: 18/12/2023

Work done today:

* Queried datasets (Kyra + Sven)
* Started data cleaning (Kyra + Sven)

Work done since the previous meeting

* Finish hypothesis refinement (Kyra + Sven)

Plans for work until the next meeting:

* Finish data cleaning (Chachi)
* Prepare the data frame (Klest)
* Start hypothesis testing (Klest)

Questions from the group:

Where should we be right now?

How do we obtain the station codes?

**Week 7:**

Date: 08/01/2024

Work done since previous meeting:

* Finish data cleaning (Chachi)(finished)
* Start preparing the data frame (Klest)->(Jiaqi) (not finished)

Plans for work until the next meeting:

* Fix logs (Klest)
* Fix agenda (Sven)
* Fix planning (Kyra)
* Create data frame (Jiaqi)
* Create slides

Questions from the group:

Is there a template for the slides?

What should we fix?

Are we on track?

Should we change the hypothesis to make a null hypothesis possible?