**Planning**

**Week 5** (**11/12/2023):**

*Get to know each other:* First, we want to get to know each other and discuss our expectations for the project. (Everyone)

*Share findings from GA1:* After getting to know each other, we want to take a look at the posters that we made for GA1. We will try to find differences and similarities in our findings, so that we can formulate different hypotheses. (Everyone)

*Hypothesis formulation:* We will first formulate three hypotheses and then do some research on these. From the research, we will choose the best hypothesis. (Everyone)

*Hypothesis refinement:* If we still have some time left, we will do some extra on our hypothesis, so that we can refine it (Kyra). We will explain our refinement (Klest).

*Logs, planning, agenda:* We have to update our logbook (Klest), agenda (Klest) and planning (Kyra).

**Week 6 (18/12/2023):**

*Finding station codes:* First, we need to find two station codes for our hypothesis, so that we can start the data queries. (Sven & Kyra)

*Data queries:* We will retrieve data about our chosen cities from the data frame with the station codes. (Jiaqi)

*Data cleaning:* We will finish cleaning the data and prepare the data frame. (Jiaqi)

*Logs, planning, agenda:* We have to update our logbook (Klest), agenda (Klest) and planning (Kyra).

**Week 7 (08/01/2024):**

*Hypothesis testing:* This week we will start doing tests. We figured that our tests weren’t completely right, so we will do another test and make visualizations of them for our pitch. (Klest & Sven)

*Pitch slides preparation:* We need to start preparing the slides for the pitch. (Kyra)

*Refining report:* We will refine the notebook, so everything looks clear in the report. (Jiaqi)

*Logs, planning, agenda:* We have to update our logbook (Klest), agenda (Sven) and planning (Kyra).

*Preparing pitch:* Preparing the pitch for Monday. (Sven & Kyra)